## P24 Commercial Center - JC Data
P24 Commercial Center - JC Data Center Setup and Migration Wave Plan.mpp | [12 empty] | 2021-03-10 17:18
| WBS Number | [6 empty] | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Status | Priority | Task description | Cost | Actual cost | Created | Type | Level
| 1 | P24 Commercial Center - JC Data Center Setup and Migration Wave Plan (DRAFT) | [7 empty] | 2020-07-07 08:00 | 2022-03-23 17:00 |  | 12 | 3576 |  |  |  | 0 | 0 | 2021-03-10 11:16 | project | 1
| 1.1 |  | PLANNING | [6 empty] | 2020-07-07 08:00 | 2022-01-14 17:00 |  | 22 | 3192 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 2
| 1.1.1 |  |  | Workstream Program | [5 empty] | 2020-07-07 08:00 | 2021-01-29 17:00 |  | 49 | 1192 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 3
| 1.1.1.1 |  |  |  | Initial Program Migration Strategy |  |  |  |  | 2020-07-07 08:00 | 2020-07-17 17:00 |  | 100 | 72 | Done | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 4
| 1.1.1.2 |  |  |  | Funding Approved |  |  |  |  | 2020-09-17 08:00 | 2020-09-17 17:00 |  | 100 | 8 | Done | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 4
| 1.1.1.3 |  |  |  | Resources/Staffing Commercial Center |  |  |  |  | 2020-11-30 08:00 | 2021-01-29 17:00 |  | 56 | 360 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 4
| 1.1.1.3.1 |  |  |  |  | QA Team |  |  |  | 2020-11-30 08:00 | 2021-01-29 17:00 |  | 50 | 360 | In progress | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.1.1.3.2 |  |  |  |  | Soft Dev Team |  |  |  | 2020-11-30 08:00 | 2020-12-31 17:00 |  | 100 | 192 | Done | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.1.1.3.3 |  |  |  |  | Implementations Team |  |  |  | 2020-11-30 08:00 | 2020-12-31 17:00 |  | 100 | 192 | Done | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.1.1.3.4 |  |  |  |  | Ops/Dev Implementations Team |  |  |  | 2020-11-30 08:00 | 2021-01-29 17:00 |  | 25 | 360 | In progress | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.1.1.3.5 |  |  |  |  | Networking Team |  |  |  | 2020-11-30 08:00 | 2021-01-29 17:00 |  | 50 | 360 | In progress | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.1.1.4 |  |  |  | Refine ESF, NonESF, PKS Migration Strategy |  |  |  |  | 2020-12-01 08:00 | 2021-01-29 17:00 |  | 30 | 352 | In progress | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 4
| 1.1.2 |  |  | Other Dependencies | [5 empty] | 2021-05-03 08:00 | 2022-01-14 17:00 |  | 0 | 1480 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 3
| 1.1.2.1 |  |  |  | JC data center build out, ESF, PKS, Data Xchange, etc. |  |  |  |  | 2021-06-30 08:00 | 2021-06-30 08:00 |  | 0 | 0 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | milestone | 4
| 1.1.2.2 |  |  |  | PROD Freeze Periods. |  |  |  |  | 2021-12-20 08:00 | 2022-01-14 17:00 |  | 0 | 160 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 4
| 1.1.2.2.1 |  |  |  |  | End of year. |  |  |  | 2021-12-20 08:00 | 2022-01-14 17:00 |  | 0 | 160 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.1.2.3 |  |  |  | Onboarding. |  |  |  |  | 2021-05-03 08:00 | 2021-06-30 17:00 |  | 0 | 344 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 4
| 1.2 |  | EXECUTION | [6 empty] | 2021-01-01 08:00 | 2022-03-23 17:00 |  | 0 | 2552 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 2
| 1.2.1 |  |  | CC JC Infrastructure | [5 empty] | 2021-01-01 08:00 | 2021-06-30 17:00 |  | 0 | 1032 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 3
| 1.2.1.1 |  |  |  | Procure hardware |  |  |  |  | 2021-01-01 08:00 | 2021-02-11 17:00 |  | 0 | 240 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 4
| 1.2.1.2 |  |  |  | Build lower environments |  |  |  |  | 2021-02-12 08:00 | 2021-03-11 17:00 |  | 0 | 160 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 4
| 1.2.1.3 |  |  |  | Build upper environments |  |  |  |  | 2021-02-26 08:00 | 2021-03-25 17:00 |  | 0 | 160 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 4
| 1.2.1.4 |  |  |  | F/W & L/B |  |  |  |  | 2021-03-12 08:00 | 2021-04-15 17:00 |  | 0 | 200 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 4
| 1.2.1.5 |  |  |  | Monitoring and Automation |  |  |  |  | 2021-04-01 08:00 | 2021-06-30 17:00 |  | 0 | 520 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 4
| 1.2.1.6 |  |  |  | Migrate infrastructure for services (SMS, Fax, File) |  |  |  |  | 2021-04-01 08:00 | 2021-06-30 17:00 |  | 0 | 520 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 4
| 1.2.2 |  |  | CC JC Application Set up | [5 empty] | 2021-01-01 08:00 | 2021-06-30 17:00 |  | 0 | 1032 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 3
| 1.2.2.1 |  |  |  | Development of CC v21.2 (App Modernization) |  |  |  |  | 2021-01-01 08:00 | 2021-06-30 17:00 |  | 0 | 1032 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 4
| 1.2.2.2 |  |  |  | ESF Networking |  |  |  |  | 2021-01-19 08:00 | 2021-01-29 17:00 |  | 0 | 72 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 4
| 1.2.2.2.1 |  |  |  |  | Connectivity to ESF Cores |  |  |  | 2021-01-19 08:00 | 2021-01-22 17:00 |  | 0 | 32 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.2.2.1.1 | [5 empty] | Information Gathering & Discovery for network paths |  |  | 2021-01-19 08:00 | 2021-01-19 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.2.2.1.2 | [5 empty] | Request Connectivity from FTS |  |  | 2021-01-20 08:00 | 2021-01-20 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.2.2.1.3 | [5 empty] | Allow Connectivity from Commercial Center |  |  | 2021-01-21 08:00 | 2021-01-21 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.2.2.1.4 | [5 empty] | Test Connections |  |  | 2021-01-22 08:00 | 2021-01-22 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.2.2.2 |  |  |  |  | ESF Implementation Dev |  |  |  | 2021-01-25 08:00 | 2021-01-29 17:00 |  | 0 | 40 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.2.2.2.1 | [5 empty] | Currently Testing PKS - 3 Implementations Bank (Moving off EFS legacy system to PKS) |  |  | 2021-01-25 08:00 | 2021-01-25 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.2.2.2.2 | [5 empty] | Migration from direct communication to ESF |  |  | 2021-01-26 08:00 | 2021-01-27 17:00 |  | 0 | 16 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 6
| 1.2.2.2.2.2.1 | [6 empty] | Update configuration to decommision Direct Connection |  | 2021-01-26 08:00 | 2021-01-26 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.2.2.2.2.2 | [6 empty] | Configure microservices in Maestro for ESF |  | 2021-01-27 08:00 | 2021-01-27 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.2.2.2.3 | [5 empty] | Migration from ESF module to ESF microservices |  |  | 2021-01-28 08:00 | 2021-01-29 17:00 |  | 0 | 16 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 6
| 1.2.2.2.2.3.1 | [6 empty] | Migrate to Microservices for ESF 8 |  | 2021-01-28 08:00 | 2021-01-28 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.2.2.2.3.2 | [6 empty] | First upgrade from version 8 to 9 before going to PKS |  | 2021-01-29 08:00 | 2021-01-29 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.2.3 |  |  |  | Inventory Dedicated Customer Networking |  |  |  |  | 2021-02-01 08:00 | 2021-02-12 17:00 |  | 0 | 80 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 4
| 1.2.2.3.1 |  |  |  |  | Inventory dedicated customer networking - VPNs? Circuits? |  |  |  | 2021-02-01 08:00 | 2021-02-01 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.2.3.2 |  |  |  |  | -Review and verify connections to migrate |  |  |  | 2021-02-02 08:00 | 2021-02-02 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.2.3.3 |  |  |  |  | -Discovery: Connectivity options |  |  |  | 2021-02-03 08:00 | 2021-02-03 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.2.3.4 |  |  |  |  | -Start conversations with clients to migrate connectivity |  |  |  | 2021-02-04 08:00 | 2021-02-04 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.2.3.5 |  |  |  |  | -Create migration plans for each client |  |  |  | 2021-02-05 08:00 | 2021-02-05 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.2.3.6 |  |  |  |  | Migrate dedicated customer networking to JC (25) |  |  |  | 2021-02-08 08:00 | 2021-02-08 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.2.3.7 |  |  |  |  | Create test suite for customer and validate |  |  |  | 2021-02-09 08:00 | 2021-02-09 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.2.3.8 |  |  |  |  | -Request proposals and quotes |  |  |  | 2021-02-10 08:00 | 2021-02-10 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.2.3.9 |  |  |  |  | -Client sign proposal |  |  |  | 2021-02-11 08:00 | 2021-02-11 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.2.3.10 |  |  |  |  | -Connectivity implementation |  |  |  | 2021-02-12 08:00 | 2021-02-12 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.2.4 |  |  |  | File Feed Handling |  |  |  |  | 2021-02-15 08:00 | 2021-02-17 17:00 |  | 0 | 24 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 4
| 1.2.2.4.1 |  |  |  |  | Identify file source for customer |  |  |  | 2021-02-15 08:00 | 2021-02-15 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.2.4.2 |  |  |  |  | Migrate to SFG and validate |  |  |  | 2021-02-16 08:00 | 2021-02-16 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.2.4.3 |  |  |  |  | Migrate any banking at FTP to decided destination |  |  |  | 2021-02-17 08:00 | 2021-02-17 17:00 |  | 0 | 8 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.2.5 |  |  |  | DEV Migration Waves |  |  |  |  | 2021-04-01 08:00 | 2021-06-23 17:00 |  | 0 | 480 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 4
| 1.2.2.5.1 |  |  |  |  | DEV WAVE 1 |  |  |  | 2021-04-01 08:00 | 2021-04-07 17:00 |  | 0 | 40 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.2.5.1.1 | [5 empty] | Create CERT environments - 2 banks per developer per week for 4 developers. |  |  | 2021-04-01 08:00 | 2021-04-07 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.2.5.2 |  |  |  |  | DEV WAVE 2 |  |  |  | 2021-04-08 08:00 | 2021-04-14 17:00 |  | 0 | 40 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.2.5.2.1 | [5 empty] | Create CERT environments - 2 banks per developer per week for 4 developers. |  |  | 2021-04-08 08:00 | 2021-04-14 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.2.5.3 |  |  |  |  | DEV WAVE 3 |  |  |  | 2021-04-15 08:00 | 2021-04-21 17:00 |  | 0 | 40 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.2.5.3.1 | [5 empty] | Create CERT environments - 2 banks per developer per week for 4 developers. |  |  | 2021-04-15 08:00 | 2021-04-21 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.2.5.4 |  |  |  |  | DEV WAVE 4 |  |  |  | 2021-04-22 08:00 | 2021-04-28 17:00 |  | 0 | 40 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.2.5.4.1 | [5 empty] | Create CERT environments - 2 banks per developer per week for 4 developers. |  |  | 2021-04-22 08:00 | 2021-04-28 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.2.5.5 |  |  |  |  | DEV WAVE 5 |  |  |  | 2021-04-29 08:00 | 2021-05-05 17:00 |  | 0 | 40 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.2.5.5.1 | [5 empty] | Create CERT environments - 2 banks per developer per week for 4 developers. |  |  | 2021-04-29 08:00 | 2021-05-05 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.2.5.6 |  |  |  |  | DEV WAVE 6 |  |  |  | 2021-05-06 08:00 | 2021-05-12 17:00 |  | 0 | 40 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.2.5.6.1 | [5 empty] | Create CERT environments - 2 banks per developer per week for 4 developers. |  |  | 2021-05-06 08:00 | 2021-05-12 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.2.5.7 |  |  |  |  | DEV WAVE 7 |  |  |  | 2021-05-13 08:00 | 2021-05-19 17:00 |  | 0 | 40 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.2.5.7.1 | [5 empty] | Create CERT environments - 2 banks per developer per week for 4 developers. |  |  | 2021-05-13 08:00 | 2021-05-19 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.2.5.8 |  |  |  |  | DEV WAVE 8 |  |  |  | 2021-05-20 08:00 | 2021-05-26 17:00 |  | 0 | 40 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.2.5.8.1 | [5 empty] | Create CERT environments - 2 banks per developer per week for 4 developers. |  |  | 2021-05-20 08:00 | 2021-05-26 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.2.5.9 |  |  |  |  | DEV WAVE 9 |  |  |  | 2021-05-27 08:00 | 2021-06-02 17:00 |  | 0 | 40 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.2.5.9.1 | [5 empty] | Create CERT environments - 2 banks per developer per week for 4 developers. |  |  | 2021-05-27 08:00 | 2021-06-02 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.2.5.10 |  |  |  |  | DEV WAVE 10 |  |  |  | 2021-06-03 08:00 | 2021-06-09 17:00 |  | 0 | 40 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.2.5.10.1 | [5 empty] | Create CERT environments - 2 banks per developer per week for 4 developers. |  |  | 2021-06-03 08:00 | 2021-06-09 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.2.5.11 |  |  |  |  | DEV WAVE 11 (Catch up) |  |  |  | 2021-06-10 08:00 | 2021-06-16 17:00 |  | 0 | 40 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.2.5.11.1 | [5 empty] | Create CERT environments - 2 banks per developer per week for 4 developers. |  |  | 2021-06-10 08:00 | 2021-06-16 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.2.5.12 |  |  |  |  | DEV WAVE 12 (Catch up) |  |  |  | 2021-06-17 08:00 | 2021-06-23 17:00 |  | 0 | 40 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.2.5.12.1 | [5 empty] | Create CERT environments - 2 banks per developer per week for 4 developers. |  |  | 2021-06-17 08:00 | 2021-06-23 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3 |  |  | Customer Migration Waves | [5 empty] | 2021-06-17 08:00 | 2022-03-23 17:00 |  | 0 | 1600 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 3
| 1.2.3.1 |  |  |  | Cust WAVE 1 (18 ESF) |  |  |  |  | 2021-06-17 08:00 | 2021-09-22 17:00 |  | 0 | 560 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 4
| 1.2.3.1.1 |  |  |  |  | Obtain schedule alignment with banks. |  |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.3.1.1.1 | [5 empty] | Atlantic Capital Bank |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.2 | [5 empty] | Banc of California |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.3 | [5 empty] | Bridgewater Bank |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.4 | [5 empty] | Dominion BancShares |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.5 | [5 empty] | Enterprise Bank |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.6 | [5 empty] | First Mid-Illinois Bank and Trust |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.7 | [5 empty] | Heritage Bank of Commerce |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.8 | [5 empty] | LakeLand |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.9 | [5 empty] | Montecito Bank & Trust |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.10 | [5 empty] | Morton Community Bank |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.11 | [5 empty] | NorthWest Bank |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.12 | [5 empty] | Oakwood Bank |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.13 | [5 empty] | Opus Bank |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.14 | [5 empty] | South State Bank |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.15 | [5 empty] | Starion Bank |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.16 | [5 empty] | Stifel Bank |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.17 | [5 empty] | Sunwest |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.1.18 | [5 empty] | TBK Bank |  |  | 2021-06-17 08:00 | 2021-06-30 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.1.2 |  |  |  |  | Internal testing and validation. |  |  |  | 2021-07-01 08:00 | 2021-08-04 17:00 |  | 0 | 200 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.3.1.3 |  |  |  |  | Bank validation. |  |  |  | 2021-08-05 08:00 | 2021-09-08 17:00 |  | 0 | 200 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.3.1.4 |  |  |  |  | Production Buildout |  |  |  | 2021-09-09 08:00 | 2021-09-15 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.3.1.5 |  |  |  |  | Prod validation |  |  |  | 2021-09-16 08:00 | 2021-09-22 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.3.2 |  |  |  | Cust WAVE 2 (8 ESF, 10 DC) |  |  |  |  | 2021-08-19 08:00 | 2021-11-24 17:00 |  | 0 | 560 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 4
| 1.2.3.2.1 |  |  |  |  | Data Center Only |  |  |  | 2021-08-19 08:00 | 2021-10-27 17:00 |  | 0 | 400 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.3.2.1.1 | [5 empty] | Obtain schedule alignment with banks. |  |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 6
| 1.2.3.2.1.1.1 | [6 empty] | Suntrust |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.1.1.2 | [6 empty] | Bank of Hawaii |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.1.1.3 | [6 empty] | City National Bank |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.1.1.4 | [6 empty] | EastWest Bank |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.1.1.5 | [6 empty] | First Hawaiian |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.1.1.6 | [6 empty] | WoodForest National Bank |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.1.1.7 | [6 empty] | Peoples Bank |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.1.1.8 | [6 empty] | Capital One Bank |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.1.1.9 | [6 empty] | HancockWhitney Bank |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.1.1.10 | [6 empty] | First Republic |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.1.2 | [5 empty] | Internal testing and validation. |  |  | 2021-09-02 08:00 | 2021-09-08 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.2.1.3 | [5 empty] | Bank validation. |  |  | 2021-09-09 08:00 | 2021-10-13 17:00 |  | 0 | 200 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.2.1.4 | [5 empty] | Production Buildout |  |  | 2021-10-14 08:00 | 2021-10-20 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.2.1.5 | [5 empty] | Prod Validation |  |  | 2021-10-21 08:00 | 2021-10-27 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.2.2 |  |  |  |  | ESF |  |  |  | 2021-08-19 08:00 | 2021-11-24 17:00 |  | 0 | 560 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.3.2.2.1 | [5 empty] | Obtain schedule alignment with banks. |  |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 6
| 1.2.3.2.2.1.1 | [6 empty] | Wallis State Bank |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.2.1.2 | [6 empty] | Bank United |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.2.1.3 | [6 empty] | Broadway Bank |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.2.1.4 | [6 empty] | Central Pacific |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.2.1.5 | [6 empty] | Merchants Bank |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.2.1.6 | [6 empty] | Sterling National Bank |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.2.1.7 | [6 empty] | TriState Capital Bank |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.2.1.8 | [6 empty] | Old National Bank |  | 2021-08-19 08:00 | 2021-09-01 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 7
| 1.2.3.2.2.2 | [5 empty] | Internal testing and validation. |  |  | 2021-09-02 08:00 | 2021-10-06 17:00 |  | 0 | 200 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.2.2.3 | [5 empty] | Bank validation. |  |  | 2021-10-07 08:00 | 2021-11-10 17:00 |  | 0 | 200 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.2.2.4 | [5 empty] | Production Buildout |  |  | 2021-11-11 08:00 | 2021-11-17 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.2.2.5 | [5 empty] | Prod Validation |  |  | 2021-11-18 08:00 | 2021-11-24 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3 |  |  |  | Cust WAVE 3 (18 DC) |  |  |  |  | 2021-10-21 08:00 | 2022-01-28 17:00 |  | 0 | 576 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 4
| 1.2.3.3.1 |  |  |  |  | Obtain schedule alignment with banks. |  |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.3.3.1.1 | [5 empty] | Santander |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.2 | [5 empty] | Santander - Santander Link |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.3 | [5 empty] | American National Bank of TX |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.4 | [5 empty] | Axos Bank/bofi |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.5 | [5 empty] | Bank Rhode Island - Brookline |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.6 | [5 empty] | Brookline Bank |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.7 | [5 empty] | First Ipswich Bank - Brookline |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.8 | [5 empty] | First US Bank |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.9 | [5 empty] | Great Western Bank |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.10 | [5 empty] | Iberia Bank |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.11 | [5 empty] | Servis1st Bank |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.12 | [5 empty] | Univest (Fox Chase) |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.13 | [5 empty] | Coast 360 FCU |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.14 | [5 empty] | Hawaii USA |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.15 | [5 empty] | TechCU |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.16 | [5 empty] | Bancorp South |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.17 | [5 empty] | TD Bank |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.1.18 | [5 empty] | Bank of Oklahoma |  |  | 2021-10-21 08:00 | 2021-11-03 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.3.2 |  |  |  |  | Internal testing and validation. |  |  |  | 2021-11-04 08:00 | 2021-11-10 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.3.3.3 |  |  |  |  | Bank validation. |  |  |  | 2021-11-11 08:00 | 2021-12-15 17:00 |  | 0 | 200 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.3.3.4 |  |  |  |  | Production Buildout |  |  |  | 2022-01-17 08:00 | 2022-01-21 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.3.3.5 |  |  |  |  | Prod validation |  |  |  | 2022-01-24 08:00 | 2022-01-28 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.3.4 |  |  |  | Cust WAVE 4 (1 DC, 17 PKS) |  |  |  |  | 2021-12-02 08:00 | 2022-02-09 17:00 |  | 0 | 400 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 4
| 1.2.3.4.1 |  |  |  |  | Obtain schedule alignment with banks. |  |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.3.4.1.1 | [5 empty] | Regions |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.2 | [5 empty] | Metropolitan Commercial Bank |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.3 | [5 empty] | California Bank of Commerce |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.4 | [5 empty] | Carter Bank and Trust |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.5 | [5 empty] | DIME Bank |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.6 | [5 empty] | First Financial NorthWest |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.7 | [5 empty] | First Security Bank |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.8 | [5 empty] | Freedom Bank |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.9 | [5 empty] | NYCB (P24) |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.10 | [5 empty] | Salem 5 |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.11 | [5 empty] | WAFED (Washington Federal, Inc.) |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.12 | [5 empty] | First Foundation Bank |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.13 | [5 empty] | West Texas Bank |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.14 | [5 empty] | DIME Bank (formerly known as BNB Bank) |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.15 | [5 empty] | Mechanics Bank |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.16 | [5 empty] | The Park National Bank |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.17 | [5 empty] | Alerus Bank |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.1.18 | [5 empty] | Old National Bank |  |  | 2021-12-02 08:00 | 2021-12-15 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.4.2 |  |  |  |  | Internal testing and validation. |  |  |  | 2021-12-16 08:00 | 2021-12-22 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.3.4.3 |  |  |  |  | Bank validation. |  |  |  | 2021-12-23 08:00 | 2022-01-26 17:00 |  | 0 | 200 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.3.4.4 |  |  |  |  | Production Buildout |  |  |  | 2022-01-27 08:00 | 2022-02-02 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.3.4.5 |  |  |  |  | Prod Validation |  |  |  | 2022-02-03 08:00 | 2022-02-09 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.3.5 |  |  |  | Cust WAVE 5 (7 PKS) |  |  |  |  | 2022-01-13 08:00 | 2022-03-23 17:00 |  | 0 | 400 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 4
| 1.2.3.5.1 |  |  |  |  | Obtain schedule alignment with banks. |  |  |  | 2022-01-13 08:00 | 2022-01-26 17:00 |  | 0 | 80 |  |  |  | 0 | 0 | 2021-03-10 11:16 | tasks group | 5
| 1.2.3.5.1.1 | [5 empty] | Sunflower Bank, NA |  |  | 2022-01-13 08:00 | 2022-01-26 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.5.1.2 | [5 empty] | First Foundation Bank |  |  | 2022-01-13 08:00 | 2022-01-26 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.5.1.3 | [5 empty] | Independent Bank |  |  | 2022-01-13 08:00 | 2022-01-26 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.5.1.4 | [5 empty] | CFG Community Bank |  |  | 2022-01-13 08:00 | 2022-01-26 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.5.1.5 | [5 empty] | Prosperity (P24) |  |  | 2022-01-13 08:00 | 2022-01-26 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.5.1.6 | [5 empty] | HomeTrust Bank |  |  | 2022-01-13 08:00 | 2022-01-26 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.5.1.7 | [5 empty] | TriCounties Bank |  |  | 2022-01-13 08:00 | 2022-01-26 17:00 |  | 0 | 80 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 6
| 1.2.3.5.2 |  |  |  |  | Internal testing and validation. |  |  |  | 2022-01-27 08:00 | 2022-02-02 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.3.5.3 |  |  |  |  | Bank validation. |  |  |  | 2022-02-03 08:00 | 2022-03-09 17:00 |  | 0 | 200 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.3.5.4 |  |  |  |  | Production Buildout |  |  |  | 2022-03-10 08:00 | 2022-03-16 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5
| 1.2.3.5.5 |  |  |  |  | Prod Validation |  |  |  | 2022-03-17 08:00 | 2022-03-23 17:00 |  | 0 | 40 | Open | Medium |  | 0 | 0 | 2021-03-10 11:16 | task | 5